## MDL 150 MLD STP V Valley-R1
| DOCUMENT NAME | [6 empty] | MASTER DOCUMENTS LIST (MDL)
| PROJECT | [6 empty] | 150 MLD STP V VALLEY
| CLIENT | [6 empty] | BANGALORE WATER SUPPLY AND SEWERAGE BOARD
| CONTRACTOR | [6 empty] | VISHVARAJ ENVIRONMENT PVT. LTD.
| Revision No./ Date | [6 empty] | R1 / 04-09-2023
Phase | S.No. | Drawing No. | [5 empty] | Title | Category of Submission | Type of Document | TaskUID | CategoryUID | Target Date | Target Date
| General Drawing/Documents | [11 empty] | 2023-09-15 | 15/09/2023
Y | 1 | 3064/ | 23-24/ | GEN/ | DOC | 1 |  | Methodology for Existing Plant Running and Bypass arrangement | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-09-15 | 15/09/2023
Y | 2 | 3064/ | 23-24/ | GEN/ | DWG | 2 |  | Topographical Survey Layout Plan | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-07-10 | 10/07/2023
Y | 3 | 3064/ | 23-24/ | GEN/ | DOC | 3 |  | Soil Investigation Report | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-07-25 | 25/07/2023
Y | 4 | 3064/ | 23-24/ | GEN/ | DOC | 4 |  | Operation & Manitenance Manual | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2024-06-11 | 11/06/2024
Y | 5 | 3064/ | 23-24/ | GEN/ | DOC | 5 |  | Training Program and Manual | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2024-05-27 | 27/05/2024
Y | 6 | 3064/ | 23-24/ | GEN/ | DOC | 6 |  | Hazop Study and Report | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2024-02-18 | 18/02/2024
Y | 7 | 3064/ | 23-24/ | GEN/ | DOC | 7 |  | Work Program/ Construction Program | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-06-13 | 13/06/2023
Y | 8 | 3064/ | 23-24/ | GEN/ | DOC | 8 |  | Tentative Cash Flow including Price Breakup | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-08-11 | 11/08/2023
Y | 9 | 3064/ | 23-24/ | GEN/ | DOC | 9 |  | Tentative Resource Mobilization Plan | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-07-10 | 10/07/2023
Y | 10 | 3064/ | 23-24/ | GEN/ | DOC | 10 |  | Monthly Progress Reports | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-05-11 | 11/05/2023
Y | 11 | 3064/ | 23-24/ | GEN/ | DOC | 11 |  | All risks insurance Policy | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-09-15 | 15/09/2023
Y | 12 | 3064/ | 23-24/ | GEN/ | DOC | 12 |  | Environmental Management Plan | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-06-15 | 15/06/2023
Y | 13 | 3064/ | 23-24/ | GEN/ | DWG | 13 |  | General Drawings for Bore Hole location and ERT Marking plan | FOR APPROVAL | DRAWING | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-09-30 | 30/09/2023
Y | 14 | 3064/ | 23-24/ | GEN/ | DOC | 14 |  | Construction Methodology | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-09-25 | 25/09/2023
Y | 15 | 3064/ | 23-24/ | GEN/ | DOC | 15 |  | Engineering Quality Plan | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-06-15 | 15/06/2023
Y | 16 | 3064/ | 23-24/ | GEN/ | DOC | 16 |  | Civil Quality Assurance Plan | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-06-15 | 15/06/2023
Y | 17 | 3064/ | 23-24/ | GEN/ | DOC | 17 |  | HSE Manual | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-06-15 | 15/06/2023
Y | 18 | 3064/ | 23-24/ | GEN/ | DOC | 18 |  | Vendor List with Communication details for all equipment | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-11-14 | 14/11/2023
Y | 19 | 3064/ | 23-24/ | GEN/ | DOC | 19 |  | Price Schedule and Billing Break-up | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-06-26 | 26/06/2023
Y | 20 | 3064/ | 23-24/ | GEN/ | DOC | 20 |  | Process Drainage Calculations | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2024-02-12 | 12/02/2024
Y | 21 | 3064/ | 23-24/ | GEN/ | DOC | 21 |  | Design Basis Report for Civil Designin for design calculations | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-11-16 | 16/11/2023
Y | 22 | 3064/ | 23-24/ | GEN/ | DOC | 22 |  | Interlocks List | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-10-25 | 25/10/2023
Y | 23 | 3064/ | 23-24/ | GEN/ | DOC | 23 |  | MIS Vendor Credentials and Deployment Package | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-08-22 | 22/08/2023
Y | 24 | 3064/ | 23-24/ | GEN/ | DWG | 24 |  | Plant Model Drawing | FOR APPROVAL | DRAWING | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2024-04-10 | 10/04/2024
Y | 25 | 3064/ | 23-24/ | GEN/ | DOC | 25 |  | FAT Document | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-11-14 | 14/11/2023
Y | 26 | 3064/ | 23-24/ | GEN/ | DOC | 26 |  | SAT Document | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2023-11-14 | 14/11/2023
Y | 27 | 3064/ | 23-24/ | GEN/ | DOC | 27 |  | Pre-commissioning documents | FOR APPROVAL | DOCUMENT | 4bcc799b-0527-442e-b7cb-af561037256f | 6E856B4E-9B16-464E-AFAB-947F61AD3934 | 2024-04-25 | 25/04/2024
| Process Engineering Drawing/Documents | [11 empty] | 2023-11-10 | 10/11/2023
Y | 1 | 3064/ | 23-24/ | PE/ | DOC | 1 |  | Project Description and Process Description | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-11 | 11/09/2023
Y | 2 | 3064/ | 23-24/ | PE/ | DOC | 2 |  | Process Design Calculaitons | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-11 | 11/09/2023
Y | 3 | 3064/ | 23-24/ | PE/ | DOC | 3 |  | Unit Sizing calculations | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-11 | 11/09/2023
Y | 4 | 3064/ | 23-24/ | PE/ | DOC | 4 |  | Electromechanical List of Major Equipments | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-20 | 20/09/2023
Y | 5 | 3064/ | 23-24/ | PE/ | DOC | 5 |  | Hydraulic calculations | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-20 | 20/09/2023
Y | 6 | 3064/ | 23-24/ | PE/ | DOC | 6 |  | Head Calculations of Pumps | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-11-10 | 10/11/2023
Y | 7 | 3064/ | 23-24/ | PE/ | DWG | 7 |  | Process Flow Diagram | FOR APPROVAL | DRAWING | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-15 | 15/09/2023
Y | 8 | 3064/ | 23-24/ | PE/ | DWG | 8 |  | Key Plan | FOR APPROVAL | DRAWING | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-15 | 15/09/2023
Y | 9 | 3064/ | 23-24/ | PE/ | DWG | 9 |  | Layout Plan | FOR APPROVAL | DRAWING | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-11 | 11/09/2023
Y | 10 | 3064/ | 23-24/ | PE/ | DWG | 10 |  | Process and Instrumentation Diagram with Tagging Philosophy and Legend Sheets distinguished across processes in the STP. | FOR APPROVAL | DRAWING | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-15 | 15/09/2023
Y | 11 | 3064/ | 23-24/ | PE/ | DOC | 11 |  | Hydraulic Flow Diagram | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-15 | 15/09/2023
Y | 12 | 3064/ | 3064 | PE/ | DOC | 12 |  | Mass balance | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-15 | 15/09/2023
Y | 13 | 3064/ | 23-24/ | PE/ | DOC | 13 |  | Dynamic Modelling using Biowin software | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-11 | 11/09/2023
Y | 14 | 3064/ | 23-24/ | PE/ | DWG | 14 |  | Basic Landscaping details | FOR APPROVAL | DRAWING | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2024-02-12 | 12/02/2024
Y | 15 | 3064/ | 23-24/ | PE/ | DWG/DOC | 15 |  | Service Water Utility Calculation and associated Piping | FOR APPROVAL | DRAWING/ DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-12-01 | 01/12/2023
Y | 16 | 3064/ | 23-24/ | ME/ | DOC | 16 |  | Valve Schedule | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-30 | 30/09/2023
Y | 17 | 3064/ | 23-24/ | ME/ | DOC | 17 |  | Pipe Schedule | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-09-30 | 30/09/2023
Y | 18 | 3064/ | 23-24/ | ME/ | DOC | 18 |  | Gate Schedule | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2023-10-10 | 10/10/2023
Y | 19 | 3064/ | 23-24/ | ME/ | DOC | 19 |  | Lifting device Schedule | FOR APPROVAL | DOCUMENT | a1aa6305-87ba-4c09-a5cf-04f3ed01ed07 | 9C964273-9B08-41B8-8FC1-1D28D14D3A34 | 2024-03-10 | 10/03/2024
| Mechanical Drawing/Documents | [12 empty] | 00/01/1900
| GENERAL ARRANGEMENT DRAWING | [11 empty] | 2024-03-17 | 17/03/2024
Y | 1 | 3064/ | 23-24/ | ME/ | DWG | 1 |  | Mechanical G.A OF Pump House | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-03-01 | 01/03/2024
Y | 2 | 3064/ | 23-24/ | ME/ | DWG | 2 |  | Mechanical G.A. of Primary Clarifier With Tube settler | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-01-15 | 15/01/2024
Y | 3 | 3064/ | 23-24/ | ME/ | DWG | 3 |  | Mechanical G.A. of Primary Sludge Sump and Pump House | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-03-01 | 01/03/2024
Y | 4 | 3064/ | 23-24/ | ME/ | DWG | 4 |  | Mechanical GA of Primary Scum Sump and Pump House | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-03-01 | 01/03/2024
Y | 5 | 3064/ | 23-24/ | ME/ | DWG | 5 |  | Mechanical GA of Bioreactor | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2023-12-01 | 01/12/2023
Y | 6 | 3064/ | 23-24/ | ME/ | DWG | 6 |  | Mechanical G.A of Diffuser arrangement | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-01-31 | 31/01/2024
Y | 7 | 3064/ | 23-24/ | ME/ | DWG | 7 |  | Mechanical GA of RAS Sump and Pump House | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-03-01 | 01/03/2024
Y | 8 | 3064/ | 23-24/ | ME/ | DWG | 8 |  | Mechanical GA of Secondary Clarifier | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-01-31 | 31/01/2024
Y | 9 | 3064/ | 23-24/ | ME/ | DWG | 9 |  | Mechanical GA of Secondary Scum Sump and Pump House | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-03-01 | 01/03/2024
Y | 10 | 3064/ | 23-24/ | ME/ | DWG | 10 |  | Mechanical GA of Disc Filter | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-02-25 | 25/02/2024
Y | 11 | 3064/ | 23-24/ | ME/ | DWG | 11 |  | Mechanical G.A. of Chlorine Contact Tank | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2023-12-01 | 01/12/2023
Y | 12 | 3064/ | 23-24/ | ME/ | DWG | 12 |  | Mechanical G.A.of Air Blower Building | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2023-11-26 | 26/11/2023
Y | 13 | 3064/ | 23-24/ | ME/ | DWG | 13 |  | Mechanical G.A. of Chlorinator, Chlorinator scrubber system cum Tonner Room | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-02-20 | 20/02/2024
Y | 14 | 3064/ | 23-24/ | ME/ | DWG | 14 |  | Mechanical G.A. of Substation Building | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-02-08 | 08/02/2024
Y | 15 | 3064/ | 23-24/ | ME/ | DWG | 15 |  | Mechanical G.A. of MCC/Electrical Panel room | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-02-08 | 08/02/2024
Y | 16 | 3064/ | 23-24/ | ME/ | DWG | 16 |  | Mechanical G.A. of Transformer Yard | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-02-08 | 08/02/2024
Y | 17 | 3064/ | 23-24/ | ME/ | DWG | 17 |  | Mechanical G.A. of Switchgear Room | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-02-08 | 08/02/2024
Y | 18 | 3064/ | 23-24/ | ME/ | DWG | 18 |  | Mechanical G.A. of DG Room | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-02-08 | 08/02/2024
Y | 19 | 3064/ | 23-24/ | ME/ | DWG | 19 |  | Mechanical G.A. of Chemical Building | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2023-10-22 | 22/10/2023
Y | 20 | 3064/ | 23-24/ | ME/ | DWG | 20 |  | Plant Piping Layout Plan and Sections | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-03-17 | 17/03/2024
Y | 21 | 3064/ | 23-24/ | ME/ | DWG | 21 |  | Mechanical G.A of Plant water sump | FOR APPROVAL | DRAWING | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2024-03-06 | 06/03/2024
Y | 22 | 3064/ | 23-24/ | ME/ | DOC | 22 |  | Painting Specifications Mechanical Equipment and Piping | FOR APPROVAL | DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | D1722BE3-0EA6-412C-B755-57B87D538193 | 2023-11-15 | 15/11/2023
| Vendor Documents | [9 empty] | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 |  | 2024-03-11 | 11/03/2024
Y | 23 | 3064/ | 23-24/ | ME/ | DOC/DWG | 23 |  | Datasheets, GA & QAP of Primary clarifier | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-12-11 | 11/12/2023
Y | 24 | 3064/ | 23-24/ | ME/ | DOC/DWG | 24 |  | Pumps Datasheet, GA, Characteristic Curves & QAP of Primary Sludge Pumps | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-15 | 15/01/2024
Y | 25 | 3064/ | 23-24/ | ME/ | DOC/DWG | 25 |  | Datasheets, GA & QAP of Secondary clarifier | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-12-11 | 11/12/2023
Y | 26 | 3064/ | 23-24/ | ME/ | DOC/DWG | 26 |  | Datasheet, GA, Characteristic Curves & QAP of RAS Pumps | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-15 | 15/01/2024
Y | 27 | 3064/ | 23-24/ | ME/ | DOC/DWG | 27 |  | Motors Datasheet, GA, Characteristic Curves & QAP of Sub Mixers | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-11-26 | 26/11/2023
Y | 28 | 3064/ | 23-24/ | ME/ | DOC/DWG | 28 |  | Data Sheet, GA & QAP for Diffusers | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-12-11 | 11/12/2023
Y | 29 | 3064/ | 23-24/ | ME/ | DOC/DWG | 29 |  | Datasheet , GA, Characteristic Curves & QAP of Blowers | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-12-11 | 11/12/2023
Y | 30 | 3064/ | 23-24/ | ME/ | DOC/DWG | 30 |  | Data Sheet, GA, Cross Sectional View & QAP of Disc Filter | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-10 | 10/01/2024
Y | 31 | 3064/ | 23-24/ | ME/ | DOC/DWG | 31 |  | Data Sheet, GA & QAP of Alum Dosing Systems | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-02-09 | 09/02/2024
Y | 32 | 3064/ | 23-24/ | ME/ | DOC/DWG | 32 |  | Data Sheet, GA & QAP of Chlorination System incl Tonners | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-10 | 10/01/2024
Y | 33 | 3064/ | 23-24/ | ME/ | DOC/DWG | 33 |  | Data Sheet, GA & QAP of Crane, Hoist | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-03-11 | 11/03/2024
Y | 34 | 3064/ | 23-24/ | ME/ | DOC/DWG | 34 |  | Datasheet, GA & QAP of Sluice Gates | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-09 | 09/01/2024
Y | 35 | 3064/ | 23-24/ | ME/ | DOC/DWG | 35 |  | Data Sheet, GA & QAP of Butterfly Valves | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-02-28 | 28/02/2024
Y | 36 | 3064/ | 23-24/ | ME/ | DOC/DWG | 36 |  | Data Sheet, GA & QAP of Knife Gate Valves | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-02-28 | 28/02/2024
Y | 37 | 3064/ | 23-24/ | ME/ | DOC/DWG | 37 |  | Data Sheet, GA & QAP of Ball Valves | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-02-28 | 28/02/2024
Y | 38 | 3064/ | 23-24/ | ME/ | DOC/DWG | 38 |  | Data Sheet, GA & QAP of Non-return Valves | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-02-28 | 28/02/2024
Y | 39 | 3064/ | 23-24/ | ME/ | DOC/DWG | 39 |  | Data Sheet, GA & QAP of Pipes & Fittings | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-02-28 | 28/02/2024
Y | 40 | 3064/ | 23-24/ | ME/ | DOC/DWG | 40 |  | Data Sheet, GA & QAP of Degritted Sewage Pumps | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-15 | 15/01/2024
Y | 41 | 3064/ | 23-24/ | ME/ | DOC/DWG | 41 |  | Data Sheet, GA & QAP of MLR/ MLSS/ Internal Recirculation Pumps | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-15 | 15/01/2024
Y | 42 | 3064/ | 23-24/ | ME/ | DOC/DWG | 42 |  | Data Sheet, GA & QAP of Scum Pumps of Primary and Secondary Clarifier | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-15 | 15/01/2024
Y | 43 | 3064/ | 23-24/ | ME/ | DOC/DWG | 43 |  | Data Sheet, GA & QAP of Dewatering Pumps | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-15 | 15/01/2024
Y | 44 | 3064/ | 23-24/ | ME/ | DOC/DWG | 44 |  | Data Sheet, GA & QAP of Large Diameter KGV, NRV and Butterfly valves | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-12-05 | 05/12/2023
Y | 45 | 3064/ | 23-24/ | ME/ | DOC/DWG | 45 |  | Data Sheet, GA & QAP of Alum Solution preparations tanks and mixer | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-11-26 | 26/11/2023
Y | 46 | 3064/ | 23-24/ | ME/ | DOC/DWG | 46 |  | Data Sheet, GA & QAP of Telescopic Valves | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-11-25 | 25/11/2023
Y | 47 | 3064/ | 23-24/ | ME/ | DOC/DWG | 47 |  | Data Sheet, GA & QAP of Safety Showers | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-02-09 | 09/02/2024
Y | 48 | 3064/ | 23-24/ | ME/ | DOC/DWG | 48 |  | Data Sheet, GA & QAP of Solenoid Valves | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-12-10 | 10/12/2023
Y | 49 | 3064/ | 23-24/ | ME/ | DOC/DWG | 49 |  | Data Sheet, GA & QAP of Flange adapters | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-20 | 20/01/2024
Y | 50 | 3064/ | 23-24/ | ME/ | DOC/DWG | 50 |  | Data Sheet, GA & QAP of Bellows based on their MOC’s | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-20 | 20/01/2024
Y | 51 | 3064/ | 23-24/ | ME/ | DOC/DWG | 51 |  | Data Sheet, GA & QAP of Weir Plates | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-12-11 | 11/12/2023
Y | 52 | 3064/ | 23-24/ | ME/ | DOC/DWG | 52 |  | Data Sheet, GA & QAP of Sampling Pumps | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-15 | 15/01/2024
Y | 53 | 3064/ | 23-24/ | ME/ | DOC/DWG | 53 |  | Data Sheet & QAP Lining and guniting of MS Pipes | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-04-13 | 13/04/2024
Y | 54 | 3064/ | 23-24/ | ME/ | DOC | 54 |  | Data Sheet of Fire safety Equipments | FOR APPROVAL | DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2024-01-24 | 24/01/2024
Y | 55 | 3064/ | 23-24/ | ME/ | DOC/DWG | 55 |  | Data Sheet, GA & QAP of Exhaust and Ventilation Calculations and typical Drawings. | FOR APPROVAL | DRAWING/ DOCUMENT | 1fc61e06-98b4-4ecc-930b-8043905b2cd7 | A6DE4EE0-465E-4B80-A031-37813C46CFBD | 2023-12-31 | 31/12/2023
| Civil Drawing/Documents | [11 empty] | 2024-04-05 | 05/04/2024
Y | 1 | 3064/ | 23-24/ | CE/ | DWG | 1 | A | Architechtural drawing of Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-31 | 31/03/2024
Y | 2 | 3064/ | 23-24/ | CE/ | DOC | 1 | B | Design calculations of Pump House | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-31 | 31/03/2024
Y | 3 | 3064/ | 23-24/ | CE/ | DWG | 1 | C | Structural details of Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-31 | 31/03/2024
Y | 4 | 3064/ | 23-24/ | CE/ | DWG | 2 | A | Architechtural drawing of Primary Clarifier | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-02-19 | 19/02/2024
Y | 5 | 3064/ | 23-24/ | CE/ | DOC | 2 | B | Design calculations of Primary Clarifier | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-02-19 | 19/02/2024
Y | 6 | 3064/ | 23-24/ | CE/ | DWG | 2 | C | Structural details of Primary Clarifier | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-02-19 | 19/02/2024
Y | 7 | 3064/ | 23-24/ | CE/ | DWG | 3 | A | Architechtural drawing of Primary Sludge Sump and Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-04-05 | 05/04/2024
Y | 8 | 3064/ | 23-24/ | CE/ | DOC | 3 | B | Design Calculations of Primary Sludge Sump and Pump House | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 9 | 3064/ | 23-24/ | CE/ | DWG | 3 | C | Structural details of Primary Sludge Sump and Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 10 | 3064/ | 23-24/ | CE/ | DWG | 4 | A | Architechtural drawing Primary Scum Sump and Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 11 | 3064/ | 23-24/ | CE/ | DOC | 4 | B | Design Calculations of Primary Scum Sump and Pump House | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 12 | 3064/ | 23-24/ | CE/ | DWG | 4 | C | Structural details of Primary Scum Sump and Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 13 | 3064/ | 23-24/ | CE/ | DWG | 5 | A | Architechtural drawing of Bioreactor & inlet distribution channel for Bioreactor | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-01-25 | 25/01/2024
Y | 14 | 3064/ | 23-24/ | CE/ | DOC | 5 | B | Design Calculations of Bioreactor & inlet distribution channel for Bioreactor | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-01-25 | 25/01/2024
Y | 15 | 3064/ | 23-24/ | CE/ | DWG | 5 | C | Structural details of Bioreactor & inlet distribution channel for Bioreactor | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-01-25 | 25/01/2024
Y | 16 | 3064/ | 23-24/ | CE/ | DWG | 6 | A | Architechtural drawing of RAS Sump and Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 17 | 3064/ | 23-24/ | CE/ | DOC | 6 | B | Design Calculations of RAS Sump and Pump House | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 18 | 3064/ | 23-24/ | CE/ | DWG | 6 | C | Structural details of RAS Sump and Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 19 | 3064/ | 23-24/ | CE/ | DWG | 7 | A | Architechtural drawing of MLR/ MLSS/ Internal Recirculation Channels | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-01-25 | 25/01/2024
Y | 20 | 3064/ | 23-24/ | CE/ | DOC | 7 | B | Design Calculations of MLR/ MLSS/ Internal Recirculation Channels | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-01-25 | 25/01/2024
Y | 21 | 3064/ | 23-24/ | CE/ | DWG | 7 | C | Structural details of MLR/ MLSS/ Internal Recirculation Channels | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-01-25 | 25/01/2024
Y | 22 | 3064/ | 23-24/ | CE/ | DWG | 8 | A | Architechtural drawing of Secondary Clarifier | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-02-20 | 20/02/2024
Y | 23 | 3064/ | 23-24/ | CE/ | DOC | 8 | B | Design Calculations of Secondary Clarifier | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-02-20 | 20/02/2024
Y | 24 | 3064/ | 23-24/ | CE/ | DWG | 8 | C | Structural details of Secondary Clarifier | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-02-20 | 20/02/2024
Y | 25 | 3064/ | 23-24/ | CE/ | DWG | 9 | A | Architechtural drawing of Secondary Clarifier Distribution chamber | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-02-20 | 20/02/2024
Y | 26 | 3064/ | 23-24/ | CE/ | DOC | 9 | B | Design Calculations of Secondary Clarifier Distribution Chamber | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-02-20 | 20/02/2024
Y | 27 | 3064/ | 23-24/ | CE/ | DWG | 9 | C | Structural details of Secondary Clarifier Distribution chamber | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-02-20 | 20/02/2024
Y | 28 | 3064/ | 23-24/ | CE/ | DWG | 10 | A | Architechtural drawing of Secondary Scum Sump and Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 29 | 3064/ | 23-24/ | CE/ | DOC | 10 | B | Design Calculations of Secondary Scum Sump and Pump House | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 30 | 3064/ | 23-24/ | CE/ | DWG | 10 | C | Structural details of Secondary Scum Sump and Pump House | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-21 | 21/03/2024
Y | 31 | 3064/ | 23-24/ | CE/ | DWG | 11 | A | Architechtural drawing of Chlorinator cum Tonner Room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-12-21 | 21/12/2023
Y | 32 | 3064/ | 23-24/ | CE/ | DOC | 11 | B | Design Calculations of Chlorinator cum Tonner Room | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-12-21 | 21/12/2023
Y | 33 | 3064/ | 23-24/ | CE/ | DWG | 11 | C | Structural details of Chlorinator cum Tonner Room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-12-21 | 21/12/2023
Y | 34 | 3064/ | 23-24/ | CE/ | DWG | 12 | A | Architechtural drawing of Air Blower Building | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-12-16 | 16/12/2023
Y | 35 | 3064/ | 23-24/ | CE/ | DOC | 12 | B | Design Calculations of Air Blower Building | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-12-16 | 16/12/2023
Y | 36 | 3064/ | 23-24/ | CE/ | DWG | 12 | C | Structural details of Air Blower Building | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-12-16 | 16/12/2023
Y | 37 | 3064/ | 23-24/ | CE/ | DWG | 13 | A | Architechtural drawing of Disc Filter Tank | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-16 | 16/03/2024
Y | 38 | 3064/ | 23-24/ | CE/ | DOC | 13 | B | Design Calculations of Disc Filter Tank | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-16 | 16/03/2024
Y | 39 | 3064/ | 23-24/ | CE/ | DWG | 13 | C | Structural details of Disc Filter Tank | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-16 | 16/03/2024
Y | 40 | 3064/ | 23-24/ | CE/ | DWG | 14 | A | Architechtural drawing of Chlorine Contact Tank | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-12-21 | 21/12/2023
Y | 41 | 3064/ | 23-24/ | CE/ | DOC | 14 | B | Design Calculations of Chlorine Contact Tank | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-12-21 | 21/12/2023
Y | 42 | 3064/ | 23-24/ | CE/ | DWG | 14 | C | Structural details of Chlorine Contact Tank | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-12-21 | 21/12/2023
Y | 43 | 3064/ | 23-24/ | CE/ | DWG | 15 | A | Architechtural drawing of MCC/Electrical Panel room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 44 | 3064/ | 23-24/ | CE/ | DOC | 15 | B | Design Calculations of MCC/Electrical Panel room | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 45 | 3064/ | 23-24/ | CE/ | DWG | 15 | C | Structural details of MCC/Electrical Panel room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 46 | 3064/ | 23-24/ | CE/ | DWG | 16 | A | Architechtural drawing of Transformer Yard | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 47 | 3064/ | 23-24/ | CE/ | DOC | 16 | B | Design Calculations of Transformer Yard | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 48 | 3064/ | 23-24/ | CE/ | DWG | 16 | C | Structural details of Transformer Yard | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 49 | 3064/ | 23-24/ | CE/ | DWG | 17 | A | Architechtural drawing of Switchgear Room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 50 | 3064/ | 23-24/ | CE/ | DOC | 17 | B | Design Calculations of Switchgear Room | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 51 | 3064/ | 23-24/ | CE/ | DWG | 17 | C | Structural details of Switchgear Room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 52 | 3064/ | 23-24/ | CE/ | DWG | 18 | A | Architechtural drawing of DG Room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 53 | 3064/ | 23-24/ | CE/ | DOC | 18 | B | Design Calculations of DG Room | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 54 | 3064/ | 23-24/ | CE/ | DWG | 18 | C | Structural details of DG Room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 55 | 3064/ | 23-24/ | CE/ | DWG | 19 | A | Architechtural drawing of Electrical Substation Room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 56 | 3064/ | 23-24/ | CE/ | DOC | 19 | B | Design Calculations of Electrical Substation Room | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 57 | 3064/ | 23-24/ | CE/ | DWG | 19 | C | Structural details of Electrical Substation Room | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-03-25 | 25/03/2024
Y | 58 | 3064/ | 23-24/ | CE/ | DWG | 20 | A | Architechtural drawing of Admin Building | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-10-06 | 06/10/2023
Y | 59 | 3064/ | 23-24/ | CE/ | DOC | 20 | B | Design Calculations of Admin Building | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-10-06 | 06/10/2023
Y | 60 | 3064/ | 23-24/ | CE/ | DWG | 20 | C | Structural details of Admin Building | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-10-06 | 06/10/2023
Y | 61 | 3064/ | 23-24/ | CE/ | DWG | 21 | A | Architechtural drawing of Chemical Building | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-26 | 26/11/2023
Y | 62 | 3064/ | 23-24/ | CE/ | DOC | 21 | B | Design Calculations of Chemical Building | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-26 | 26/11/2023
Y | 63 | 3064/ | 23-24/ | CE/ | DWG | 21 | C | Structural details of Chemical Building | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-26 | 26/11/2023
Y | 64 | 3064/ | 23-24/ | CE/ | DWG | 22 | A | Architechtural drawing Maintenance Workshop | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 65 | 3064/ | 23-24/ | CE/ | DOC | 22 | B | Design of Maintenance Workshop | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 66 | 3064/ | 23-24/ | CE/ | DWG | 22 | C | Structural details of Maintenance Workshop | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 67 | 3064/ | 23-24/ | CE/ | DWG | 23 | A | Architechtural drawing of Security Cabin | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 68 | 3064/ | 23-24/ | CE/ | DOC | 23 | B | Design Calculations of Security Cabin | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 69 | 3064/ | 23-24/ | CE/ | DWG | 23 | C | Structural details of Security Cabin | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 70 | 3064/ | 23-24/ | CE/ | DWG | 24 | A | Architechtural drawing of Boundary Wall | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 71 | 3064/ | 23-24/ | CE/ | DOC | 24 | B | Design calculations of Boundary Wall | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 72 | 3064/ | 23-24/ | CE/ | DWG | 24 | C | Structural details of Boundary Wall | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 73 | 3064/ | 23-24/ | CE/ | DWG | 23 | A | Architechtural drawing of Retaining wall | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 74 | 3064/ | 23-24/ | CE/ | DOC | 23 | B | Design calculations of Retaining wall | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 75 | 3064/ | 23-24/ | CE/ | DWG | 23 | C | Structural details of Retaining wall | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-10 | 10/11/2023
Y | 76 | 3064/ | 23-24/ | CE/ | DWG | 24 | A | Architechtural drawing of Process Drain Layout | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-11 | 11/11/2023
Y | 77 | 3064/ | 23-24/ | CE/ | DOC | 24 | B | Design calculations of Process Drain Layout | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-11 | 11/11/2023
Y | 78 | 3064/ | 23-24/ | CE/ | DWG | 24 | C | Structural details of Process Drain Layout | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-11 | 11/11/2023
Y | 79 | 3064/ | 23-24/ | CE/ | DWG | 25 | A | Architechtural drawing of Overhead Tank | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-16 | 16/11/2023
Y | 80 | 3064/ | 23-24/ | CE/ | DOC | 25 | B | Design calculations of Overhead Tank | FOR APPROVAL | DOCUMENT | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-16 | 16/11/2023
Y | 81 | 3064/ | 23-24/ | CE/ | DWG | 25 | C | Structural details of Overhead Tank | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2023-11-16 | 16/11/2023
Y | 82 | 3064/ | 23-24/ | CE/ | DWG | 26 |  | Standard details of Pipe Encasing | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-04-01 | 01/04/2024
Y | 83 | 3064/ | 23-24/ | CE/ | DWG | 27 |  | Standard details of Pedestal for pipeline and Cable Tray | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-04-01 | 01/04/2024
Y | 84 | 3064/ | 23-24/ | CE/ | DWG | 28 |  | Standard details of Thrust Block | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-04-01 | 01/04/2024
Y | 85 | 3064/ | 23-24/ | CE/ | DWG | 29 |  | Drawing for Rain water Harvesting | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-01-28 | 28/01/2024
Y | 86 | 3064/ | 23-24/ | CE/ | DWG | 30 |  | Drawing for Site grading, Internal Roads, Pathways & drains | FOR APPROVAL | DRAWING | 9c400ef8-e5cd-4b44-bcb7-dd2b01fa33a3 | 9EF93D1B-E7B6-419B-B7F7-E1C251C700FC | 2024-01-28 | 28/01/2024
Electrical Drawing/Documents
| Electrical Sizing Documents | [11 empty] | 2024-03-14 | 14/03/2024
Y | 1 | 3064/ | 23-24/ | EE/ | DOC | 1 |  | Electrical Load List | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-11-14 | 14/11/2023
Y | 2 | 3064/ | 23-24/ | EE/ | DOC | 2 |  | Transformer sizing calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-12-05 | 05/12/2023
Y | 3 | 3064/ | 23-24/ | EE/ | DOC | 3 |  | Capacitor sizing calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-12-05 | 05/12/2023
Y | 4 | 3064/ | 23-24/ | EE/ | DOC | 4 |  | Battery Charger Sizing Calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-03-14 | 14/03/2024
Y | 5 | 3064/ | 23-24/ | EE/ | DOC | 5 |  | Earthing Calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-12-14 | 14/12/2023
Y | 6 | 3064/ | 23-24/ | EE/ | DOC | 6 |  | Lightening Protection Calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-12-14 | 14/12/2023
Y | 7 | 3064/ | 23-24/ | EE/ | DOC | 7 |  | Short Circuit/Fault Level Calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-12-29 | 29/12/2023
Y | 8 | 3064/ | 23-24/ | EE/ | DOC | 8 |  | NGR Calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-03 | 03/01/2024
Y | 9 | 3064/ | 23-24/ | EE/ | DOC | 9 |  | Bus Duct Sizing Calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-12-19 | 19/12/2023
Y | 10 | 3064/ | 23-24/ | EE/ | DOC | 10 |  | MV Power Cable Sizing Calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-24 | 24/01/2024
Y | 11 | 3064/ | 23-24/ | EE/ | DOC | 11 |  | MV Power Cable Schedule of MPS | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-24 | 24/01/2024
Y | 12 | 3064/ | 23-24/ | EE/ | DOC | 12 |  | LT Power Cable Sizing Calculation | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-24 | 24/01/2024
Y | 13 | 3064/ | 23-24/ | EE/ | DOC | 13 |  | LT Power Cable Schedule | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-24 | 24/01/2024
Y | 14 | 3064/ | 23-24/ | EE/ | DOC | 14 |  | Control Cable Schedule | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-24 | 24/01/2024
Y | 15 | 3064/ | 23-24/ | EE/ | DOC | 15 |  | Electrical Safety Items List | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-24 | 24/01/2024
Y | 16 | 3064/ | 23-24/ | EE/ | DOC | 16 |  | Fault level calculations | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-12-04 | 04/12/2023
Y | 17 | 3064/ | 23-24/ | EE/ | DOC | 17 |  | DG Sizing and Calculations | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-12-04 | 04/12/2023
Y | 18 | 3064/ | 23-24/ | EE/ | DOC | 18 |  | Voltage Dip Calculations | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-04 | 04/01/2024
Y | 19 | 3064/ | 23-24/ | EE/ | DOC | 19 |  | Co-ordination protection study | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-04 | 04/01/2024
Y | 20 | 3064/ | 23-24/ | EE/ | DOC | 20 |  | Harmonics Study | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2023-12-04 | 04/12/2023
Y | 21 | 3064/ | 23-24/ | EE/ | DOC | 21 |  | Lighting Design Calculations for all Buildings. | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | 7CBBD0FA-0EA3-468C-95BB-C65B21D8E1DF | 2024-01-19 | 19/01/2024
| Electrical Drawings & Layout | [9 empty] | f8687994-7b77-464f-a21f-42badaf53a35 |  | 2024-03-04 | 04/03/2024
Y | 22 | 3064/ | 23-24/ | EE/ | DWG | 22 |  | Overall Plant Single Line Diagram | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2023-11-19 | 19/11/2023
Y | 23 | 3064/ | 23-24/ | EE/ | DWG | 23 |  | Lighting SLD- Indoor & Outdoor | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-03-04 | 04/03/2024
Y | 24 | 3064/ | 23-24/ | EE/ | DWG | 24 |  | Overall Cable routing Layout and Section Drawing | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-03-04 | 04/03/2024
Y | 25 | 3064/ | 23-24/ | EE/ | DWG | 25 |  | Electrical Room Equiepment and Tray Layout Drawing | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 26 | 3064/ | 23-24/ | EE/ | DWG | 26 |  | Earthing Layout | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2023-10-27 | 27/10/2023
Y | 27 | 3064/ | 23-24/ | EE/ | DWG | 27 |  | Lightening Protection Layout | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2023-10-27 | 27/10/2023
Y | 28 | 3064/ | 23-24/ | EE/ | DWG | 28 |  | Indoor Lighting layout for Primary Sludge Pump House | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 29 | 3064/ | 23-24/ | EE/ | DWG | 29 |  | Indoor Lighting layout for Process Air Blower Room | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 30 | 3064/ | 23-24/ | EE/ | DWG | 30 |  | Indoor Lighting layout for Chemical Building | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 31 | 3064/ | 23-24/ | EE/ | DWG | 31 |  | Indoor Lighting layout for Electrical Panel Room | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 32 | 3064/ | 23-24/ | EE/ | DWG | 32 |  | Indoor Lighting layout for Administration, Laboratory and Scada Building | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 33 | 3064/ | 23-24/ | EE/ | DWG | 33 |  | Indoor Lighting layout for RAS Pump house | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 34 | 3064/ | 23-24/ | EE/ | DWG | 34 |  | Indoor Lighting layout for Chlorination Building | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 35 | 3064/ | 23-24/ | EE/ | DWG | 35 |  | Indoor Lighting layout for 11KV Switchgear Room | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 36 | 3064/ | 23-24/ | EE/ | DWG | 36 |  | Indoor Lighting layout for DG Room | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 37 | 3064/ | 23-24/ | EE/ | DWG | 37 |  | Indoor Lighting layout for MCC Room | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 38 | 3064/ | 23-24/ | EE/ | DWG | 38 |  | Indoor Lighting for Maintenance Workshop | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 39 | 3064/ | 23-24/ | EE/ | DWG | 39 |  | Indoor Lighting layout for Security Room | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2024-02-23 | 23/02/2024
Y | 40 | 3064/ | 23-24/ | EE/ | DWG | 40 |  | Outdoor Lighting layout | FOR APPROVAL | DRAWING | f8687994-7b77-464f-a21f-42badaf53a35 | D004D544-833E-454E-BD64-BA342C905E0D | 2023-10-27 | 27/10/2023
| Electrical Vendor Documents | [9 empty] | f8687994-7b77-464f-a21f-42badaf53a35 |  | 2024-04-08 | 08/04/2024
Y | 41 | 3064/ | 23-24/ | EE/ | DWG/DWC | 41 |  | Electrical Panel Drawing - MV Switchgear GA, SLD, BOM, Scheme and QAP | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-02-13 | 13/02/2024
Y | 42 | 3064/ | 23-24/ | EE/ | DWG/DWC | 42 |  | Electrical Panel Drawing - PMCC Panel GA, SLD, BOM, Scheme and QAP | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-02-13 | 13/02/2024
Y | 43 | 3064/ | 23-24/ | EE/ | DWG/DWC | 43 |  | Electrical Panel Drawing - MCC Panel GA, SLD, BOM, Scheme and QAP | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-02-13 | 13/02/2024
Y | 44 | 3064/ | 23-24/ | EE/ | DWG/DWC | 44 |  | Electrical Panel Drawing - VFD Panel GA, SLD, BOM, Scheme and QAP for Process Air Blowers | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-02-13 | 13/02/2024
Y | 45 | 3064/ | 23-24/ | EE/ | DWG/DWC | 45 |  | Electrical Panel Drawing - VFD Panel GA, SLD, BOM, Scheme and QAP for RAS Pumps | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-02-13 | 13/02/2024
Y | 46 | 3064/ | 23-24/ | EE/ | DWG/DWC | 46 |  | Electrical Panel Drawing - VFD Panel GA, SLD, BOM, Scheme and QAP for MLR Pumps | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-02-13 | 13/02/2024
Y | 47 | 3064/ | 23-24/ | EE/ | DWG/DWC | 47 |  | Electrical Panel Drawing - Soft Starter Panel GA, SLD, BOM, Scheme and QAP | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-02-13 | 13/02/2024
Y | 48 | 3064/ | 23-24/ | EE/ | DWG/DWC | 48 |  | Electrical Panel Drawing - APFC GA, SLD, BOM, Scheme and QAP | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-02-13 | 13/02/2024
Y | 49 | 3064/ | 23-24/ | EE/ | DWG/DWC | 49 |  | Electrical Panel Drawing - LDB's/PDB's , Street Lighting DB, GA, SLD, BOM, Scheme and QAP | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-19 | 19/03/2024
Y | 50 | 3064/ | 23-24/ | EE/ | DWG/DWC | 50 |  | Electrical Panel Drawing - LPBS GA, BOM, Scheme and QAP | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-19 | 19/03/2024
Y | 51 | 3064/ | 23-24/ | EE/ | DWG/DWC | 51 |  | Electrical Panel Drawing - DBs for Valves and Ventilation system | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-19 | 19/03/2024
Y | 52 | 3064/ | 23-24/ | EE/ | DWG/DWC | 52 |  | Technical Specification - Transformers, GTP, GA and QAP | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-05 | 05/03/2024
Y | 53 | 3064/ | 23-24/ | EE/ | DWG/DWC | 53 |  | GAD, BOM,TDS and QAP - Battery and Battery Charger | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-04-08 | 08/04/2024
Y | 54 | 3064/ | 23-24/ | EE/ | DOC | 54 |  | TDS and QAP - MV Cables | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-29 | 29/03/2024
Y | 55 | 3064/ | 23-24/ | EE/ | DOC | 55 |  | TDS and QAP - Bus Duct from Transformer to PMCC/MCC | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-01-13 | 13/01/2024
Y | 56 | 3064/ | 23-24/ | EE/ | DOC | 56 |  | TDS and QAP - LT Power and Control Cables | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-04-03 | 03/04/2024
Y | 57 | 3064/ | 23-24/ | EE/ | DOC | 57 |  | TDS and QAP - Local Control Stations | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-19 | 19/03/2024
Y | 58 | 3064/ | 23-24/ | EE/ | DOC | 58 |  | TDS and QAP - Feeder Pillars | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-29 | 29/03/2024
Y | 59 | 3064/ | 23-24/ | EE/ | DOC | 59 |  | TDS and QAP - Lighting Fixtures | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-29 | 29/03/2024
Y | 60 | 3064/ | 23-24/ | EE/ | DOC | 60 |  | TDS and QAP - Cable Trays | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-29 | 29/03/2024
Y | 61 | 3064/ | 23-24/ | EE/ | DOC | 61 |  | TDS and QAP - Lighting Poles | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-29 | 29/03/2024
Y | 62 | 3064/ | 23-24/ | EE/ | DOC | 62 |  | TDS and QAP - Earthing material | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-29 | 29/03/2024
Y | 63 | 3064/ | 23-24/ | EE/ | DOC | 63 |  | TDS and QAP - Epabx systrem | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-29 | 29/03/2024
Y | 64 | 3064/ | 23-24/ | EE/ | DWG/DWC | 64 |  | GAD, BOM,TDS and QAP - Solar panels | FOR APPROVAL | DRAWING/ DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-29 | 29/03/2024
Y | 65 | 3064/ | 23-24/ | EE/ | DOC | 65 |  | BOM and TDS - Electrical Safety Material | FOR APPROVAL | DOCUMENT | f8687994-7b77-464f-a21f-42badaf53a35 | F10D8F80-3D73-4B87-8E26-0E9192BCE549 | 2024-03-29 | 29/03/2024
Instrument Drawings / Documents
| Instrumentation Sizing Document | [11 empty] | 2024-04-22 | 22/04/2024
Y | 1 | 3064/ | 23-24/ | IE/ | DOC | 1 |  | Instrument schedule | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | 73CD2ACF-6C45-445B-8216-529C99942C41 | 2023-10-25 | 25/10/2023
Y | 2 | 3064/ | 23-24/ | IE/ | DOC | 2 |  | PLC I/O List | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | 73CD2ACF-6C45-445B-8216-529C99942C41 | 2023-11-24 | 24/11/2023
Y | 3 | 3064/ | 23-24/ | IE/ | DOC | 3 |  | Instrument Cable Schedule | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | 73CD2ACF-6C45-445B-8216-529C99942C41 | 2024-01-08 | 08/01/2024
Y | 4 | 3064/ | 23-24/ | IE/ | DOC | 4 |  | Instrument Cable Interconnection Schedule | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | 73CD2ACF-6C45-445B-8216-529C99942C41 | 2024-02-07 | 07/02/2024
Y | 5 | 3064/ | 23-24/ | IE/ | DOC | 5 |  | Junction Box Schedule | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | 73CD2ACF-6C45-445B-8216-529C99942C41 | 2024-02-02 | 02/02/2024
Y | 6 | 3064/ | 23-24/ | IE/ | DOC | 6 |  | UPS Sizing Calculation | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | 73CD2ACF-6C45-445B-8216-529C99942C41 | 2024-02-22 | 22/02/2024
Y | 7 | 3064/ | 23-24/ | IE/ | DOC | 7 |  | Cuase-Effect Diagrams | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | 73CD2ACF-6C45-445B-8216-529C99942C41 | 2024-02-22 | 22/02/2024
Y | 8 | 3064/ | 23-24/ | IE/ | DOC | 8 |  | Instrument Alarm List with Alarm Set point Document | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | 73CD2ACF-6C45-445B-8216-529C99942C41 | 2024-04-22 | 22/04/2024
| Instrumentation Documents & Drawing | [9 empty] | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b |  | 2024-03-05 | 05/03/2024
Y | 9 | 3064/ | 23-24/ | IE/ | DOC | 9 |  | Plant Control Philosophy | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | F200F3E0-5459-48CC-B82A-F8CE8CAB94F8 | 2023-10-30 | 30/10/2023
Y | 10 | 3064/ | 23-24/ | IE/ | DOC | 10 |  | PLC System Architecture | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | F200F3E0-5459-48CC-B82A-F8CE8CAB94F8 | 2023-11-14 | 14/11/2023
Y | 11 | 3064/ | 23-24/ | IE/ | DWG | 11 |  | Instrument Hook Up Diagram | FOR APPROVAL | DRAWING | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | F200F3E0-5459-48CC-B82A-F8CE8CAB94F8 | 2024-02-07 | 07/02/2024
Y | 12 | 3064/ | 23-24/ | IE/ | DOC | 12 |  | Instrument List with their Schedules | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | F200F3E0-5459-48CC-B82A-F8CE8CAB94F8 | 2023-10-25 | 25/10/2023
Y | 13 | 3064/ | 23-24/ | IE/ | DOC | 13 |  | Instrumentation FDS | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | F200F3E0-5459-48CC-B82A-F8CE8CAB94F8 | 2023-12-30 | 30/12/2023
Y | 14 | 3064/ | 23-24/ | IE/ | DOC | 14 |  | ICA FDS | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | F200F3E0-5459-48CC-B82A-F8CE8CAB94F8 | 2024-03-05 | 05/03/2024
| Instrumentation Vendor Documents | [11 empty] | 2024-03-23 | 23/03/2024
Y | 15 | 3064/ | 23-24/ | IE/ | DWG | 15 |  | PLC Panel GA Drawing and Wiring Schemes | FOR APPROVAL | DRAWING | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2023-11-14 | 14/11/2023
Y | 16 | 3064/ | 23-24/ | IE/ | DOC | 16 |  | FAT procedure & QAP for PLC | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2023-11-14 | 14/11/2023
Y | 17 | 3064/ | 23-24/ | IE/ | DOC | 17 |  | PLC datasheet | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2023-12-30 | 30/12/2023
Y | 18 | 3064/ | 23-24/ | IE/ | DOC | 18 |  | TDS and QAP - Level Instruments | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 19 | 3064/ | 23-24/ | IE/ | DOC | 18 | A | TDS and QAP - Level Transmitter | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 20 | 3064/ | 23-24/ | IE/ | DOC | 18 | B | TDS and QAP - Level Guage | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 21 | 3064/ | 23-24/ | IE/ | DOC | 18 | C | TDS and QAP - level switch | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 22 | 3064/ | 23-24/ | IE/ | DOC | 19 |  | TDS and QAP - Flow Instruments | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 23 | 3064/ | 23-24/ | IE/ | DOC | 19 | A | TDS and QAP - Flow Transmitter | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 24 | 3064/ | 23-24/ | IE/ | DOC | 19 | B | TDS and QAP - Flow Indicator | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 25 | 3064/ | 23-24/ | IE/ | DOC | 20 |  | TDS and QAP - Pressure Instruments | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 26 | 3064/ | 23-24/ | IE/ | DOC | 20 | A | TDS and QAP - Pressure Transmitter | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 27 | 3064/ | 23-24/ | IE/ | DOC | 20 | B | TDS and QAP - Pressure Indicator | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 28 | 3064/ | 23-24/ | IE/ | DOC | 20 | C | TDS and QAP - Pressure Switch | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 29 | 3064/ | 23-24/ | IE/ | DOC | 20 | D | TDS and QAP - Pressure Guage | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 29 | 3064/ | 23-24/ | IE/ | DOC | 21 |  | TDS and QAP - Temperature switch | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 30 | 3064/ | 23-24/ | IE/ | DOC | 22 |  | TDS and QAP - Analyzers at Inlet & Outlet (ORP, NH4-N, BOD AND COD) | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 31 | 3064/ | 23-24/ | IE/ | DOC | 23 |  | TDS and QAP - DO Analyzer | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 32 | 3064/ | 23-24/ | IE/ | DOC | 24 |  | TDS and QAP - Residual Chlorine Analyzer | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 33 | 3064/ | 23-24/ | IE/ | DOC | 25 |  | TDS and QAP - pH Analyzer | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 34 | 3064/ | 23-24/ | IE/ | DOC | 26 |  | TDS and QAP - Instrument Cables | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-03-23 | 23/03/2024
Y | 35 | 3064/ | 23-24/ | IE/ | DWG/DOC | 27 |  | GA,TDS and QAP - Instrument Junction Box | FOR APPROVAL | DRAWING/ DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-03-23 | 23/03/2024
Y | 36 | 3064/ | 23-24/ | IE/ | DWG/DOC | 28 |  | GA,TDS and QAP - UPS | FOR APPROVAL | DRAWING/ DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-03-18 | 18/03/2024
Y | 37 | 3064/ | 23-24/ | IE/ | DWG/DOC | 29 |  | TDS and QAP - Auto Sampler | FOR APPROVAL | DRAWING/ DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-07 | 07/02/2024
Y | 38 | 3064/ | 23-24/ | IE/ | DWG/DOC | 30 |  | GA,TDS and QAP - Instruments Enclosure | FOR APPROVAL | DRAWING/ DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-03-23 | 23/03/2024
Y | 39 | 3064/ | 23-24/ | IE/ | DOC | 31 |  | Vendor Credentials of MIS Agency and MIS Scope Document | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2023-08-22 | 22/08/2023
Y | 40 | 3064/ | 23-24/ | IE/ | DOC | 32 |  | Vendor Credentials of ICA System Integrator | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-03-20 | 20/03/2024
Y | 41 | 3064/ | 23-24/ | IE/ | DOC | 33 |  | Vendor Credentials of Lab Equipment system integrator | FOR APPROVAL | DOCUMENT | f6ee0bc5-921c-4c7c-9b66-c22c9e67765b | D6CA4502-A83F-4F46-8B48-8E7D4880FF49 | 2024-02-22 | 22/02/2024